## Effort Overview Total
Version 1
# | Category | Item Name | (Main Caracteristics) | Total Effort (Mhrs) | %
|  |  |  | 2146.8744 | 100%
1 |  | Solution Preparation | Out of scope | 0 | -
2 |  | Elicitation/Plan | Out of scope | - | -
3 |  | Analysis, Design, Build, Test | In Scope | 1951.704 | 90.91%
4 |  | Project Management | 10% | 195.1704 | 9.091%
5 |  | User Acceptance Test (UAT) | Out of scope | - | -
6 |  | Deployment on sev Devices | Out of scope | - | -
7 |  | Train the trainer/Documentation | Out of scope | - | -
8 |  | Warranty | 5% | - | -

## App , Arch Estimation
Scope:
1 | Description
2 | Description
Main Assumptions
1 | Description
2 | Description
3 | Description
4 | Description
5 | Description
[5 empty] | 15% | 30% | REF | 60%
# | Category | Reference | Item Name | (Main Caracteristics) | Analyse | Design | Coding | Test | # | 100% Normal |  | Total Item
1951.704
1 | Web APP | 1 | Design elements coding | Complex | 0.72 | 4.8 | 16 | 9.6 | 1 | 120% | 37.344
2 | Web APP | 1 | X Template instance | Medium | 0 | 0 | 160 | 0 | 1 | 200% | 320
3 | Web APP | 2 | 4 Form + JS code to access the location with incidents | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 150% | 46.68
4 | Web APP | 2 | Dynamic Report integrated | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
5 | Web APP | 2 | DB setup + DB Model | Medium | 0.36 | 2.4 | 8 | 4.8 | 1 | 100% | 15.2
6 | Web APP | 2 | Service (ex. NodeJS) for Dynamic Reports | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
5 | Web APP | 2 | Report an incident integrated | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
6 | Web APP | 2 | Service (ex. NodeJS) for reported incidents | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
| SUM | [10 empty] | 543.704
1 | Mobile App | 1 | Design elements | Simple | 1.2 | 8 | 0 | 0 | 1 | 100% | 9.2
2 | Mobile App | 1 | Very important thinsg | Medium | 0 | 0 | 160 | 0 | 1 | 200% | 320
3 | Mobile App | 2 | 4 Form + JS code to access the location with incidents | Complex | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
4 | Mobile App | 2 | Reports | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
5 | Mobile App | 2 | Firestore | Medium | 0.36 | 2.4 | 8 | 4.8 | 1 | 100% | 15.2
6 | Mobile App | 2 | Service | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
5 | Mobile App | 2 | Report an incident | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
6 | Mobile App | 2 | Service (ex. NodeJS) II | Medium | 0.72 | 4.8 | 16 | 9.6 | 1 | 100% | 31.12
| SUM | [10 empty] | 500
|  |  |  | User Stories as effort |  |  | Effort |  | # | 100% Normal
1 | 3 party server | 5 | Design elements | Simple |  |  | 32 |  | 1 | 100% | 32
2 | 3 party server | 6 | Very important thing | Medium |  |  | 160 |  | 1 | 120% | 192
3 | 3 party server | 7 | 4 Form + JS code to access the location with incidents | Complex |  |  | 16 |  | 1 | 100% | 16
4 | 3 party server | 8 | Reports | Medium |  |  | 16 |  | 1 | 100% | 16
5 | 3 party server | 9 | Firestore | Medium |  |  | 8 |  | 1 | 100% | 8
6 | 3 party server | 12 | Service | Medium |  |  | 32 |  | 1 | 100% | 32
5 | 3 party server | 13 | Report an incident | Medium |  |  | 32 |  | 1 | 100% | 32
6 | 3 party server | 14 | Service (ex. NodeJS) II | Medium |  |  | 48 |  | 1 | 100% | 48
| SUM | [10 empty] | 376
Other elements
0
1 | Deployment at the customer | [9 empty] | 32
| Sum | [10 empty] | 32
Architecture
[7 empty] | Effort |  | # | 100% Normal
1 | Architecture 2 | [5 empty] | 200 |  | 1 | 100% | 200 | 0
2 | Architecture 1 | [5 empty] | 150 |  | 1 | 200% | 300
| Sum | [10 empty] | 500

## Pre, Elic, PM, UAT, Warranty
# | Category | Item Name - SOL PREPARATION | (Main Caracteristics) | Effort | 100% Normal | Total Item
0
1 | ANALYSIS | Analysis of specifications, client materials | Out of Scope | - | 100% | 0
`
# | Category | Item Name - ELICITATION | (Main Caracteristics) | Effort | 100% Normal | Total Item
0
`
1 | ANALYSIS | Analysis of specifications, client materials | Out of scope | - | 100% | 0
2 | ANALYSIS | Screen mockups | Out of scope | - | 100% | 0
3 | ANALYSIS | Effort Estimation | Out of scope | - | 100% | 0
3 | ANALYSIS | Agreement of the scope with customer | Out of scope | - | 100% | 0
# | Category | Item Name - PM | (Main Caracteristics) | % of Effort | Other risk? | Total Item
195.1704
1 | PM | Project Management |  | 10% |  | 195.1704
# | Category | Item Name - UAT | (Main Caracteristics) | Effort | 100% Normal | Total Item
80
1 | UAT | Prepare the test cases, agree with customer | out of scope | 80 | 100% | 80
2 | UAT | Client side setup of DB connection, Maintenance Server, Terminal Server | out of scope | - | 200% | 0
3 | UAT | Demo at supplier (client at Skype?) On-site testing, fixing if necessary. | out of scope | - | 200% | 0
# | Category | Item Name - Warranty-Training | (Main Caracteristics) | Effort | 100% Normal | Total Item
97.5852
1 | SUPPORT | Training of the trainers | out of scope | -
2 | SUPPORT | Warranty effort included in the base estimation | 5% |  | 5% | 97.5852
3 | SUPPORT | 2 Weeks support after Live Go included | out of scope | -
4 | SUPPORT | Deployment activities for XX devices on client premises included | out of scope | -

## Scheduling, Price
| 1 Week | 34 | hrs
1 Months
1 | PM | 20
2 | Architect | 34 | EUR/hrs
3 | Soft-Eng #1 | 45 | EUR/hrs
4 | Developer #2 | 56 | EUR/hrs
5 | Developer #3 | 56 | EUR/hrs
6 | Developer #4 | 34 | EUR/hrs
|  |  | EUR/hrs |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May
|  |  |  | Start Date | 4413700% | 4414400% | 4415100% | 4415800% | 4416500% | 4417200% | 4417900% | 4418600% | 4419300% | 4420000% | 4420700% | 4421400% | 4422100% | 4422800% | 4423500% | 4424200% | 4424900% | 4425600% | 4426300% | 4427000% | 4427700% | 4428400% | 4429100% | 4429800% | 4430500% | 4431200% | 4431900% | 4432600% | 4433300% | 4434000% | 4434700% | 4435400% | 4436100% | 4436800% | 4437500% | 4438200% | 4438900% | 4439600% | 4440300%
|  |  |  | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[17 empty] | Start |  |  |  |  | M1 |  |  |  |  | M2
|  |  | Effort | 2142
| A/Des/ Buid/Test | PM |  | 10880 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Architect |  | 18496 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Soft-Eng #1 |  | 22950 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5
|  | Developer #2 |  | 19040 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Developer #3 |  | 11424 |  |  | 1 | 1 | 1 | 1 | 1 | 1
|  | Developer #4 |  | 0
|  |  | Effort | 34
| Deploy | Soft-Eng #1 |  | 1530 | [23 empty] | 1
0
|  |  |  | #FTE | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Effort without Warranty |  | Effort | 2176
| Price without Warranty |  | Price | 84320
| Warranty (calculated) |  | Effort | 97.5852
| Total Effort with Warranty |  | Effort | 2273.5852
| Total Price with Warranty | Developer #2 |  | 88711.334
| Fix Price/ Responsibility |  |  | 7%
| Other Risk / Neg Contingency |  |  | 0%
| My Company Fixed Price |  | Price | 94921.1274
| External Supplier Price |  | Price | 1000
| Fixed Assets (Tools, license ...) |  |  | 200
| My Company + Supplier Price |  |  | 96121.1274
Fix Price/ Responsibility |  | 0% | 5% | 10%
Other Risk / Neg Contingency |  | 5% | 5% | 5%
Fixed Price |  | 93146.9007 | 97582.4674 | 102018.0341
AVG Hourly rate |  | 40.9692 | 42.9201 | 44.871